## Task Breakdown
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Create user stories list | 2025-03-14 | 2025-03-15
2 | Create the task breakdown | 2025-03-15
3 | Research similar websites + design | 2025-03-18
4 | choose fonts, colors, branding elements | 2025-03-18
5 | create wireframs for all the pages | 2025-03-18
6 | make a site map and navigation srucutre | 2025-03-18
7 | create folders for the project like static, view, index.html, etc | 2025-03-18
8 | make a homepage for the website | 2025-03-18
9 | create additional pages like about, tickets, contact | 2025-03-23
10 | make a navigation bar and footer | 2025-03-23
11 | integrate google maps api + javascript + jquery | 2025-03-24
12 | make the contact form | 2025-03-24
13 | test the website and get feedback | 2025-03-26
14 | make final revisions and submit project | 2025-03-28
15
...